## Slide 1: Infographics on JU Admission Test Process
A Bit to Byte Production House

## Slide 2: OUR TEAM
Rifat Ara
Shahrin Khan
Ikramul Islam Emon
Md Anayet Ullah
Israt Jahan Munny
Md Asoad Alvi Yanur Saom
Jannatul Ferdaws Amrin

## Slide 3: Problem Statement
The crucial part for an examinee is to
  understand the requirements of applying.
  understand the correct information on each unit.
However, an unorganized and poorly visualized document causes a variety of issues, including -
  Missing crucial facts.
  Conflict with the requirements of one unit to other units.
  Not understanding the comprehend all of the points made in documents.

## Slide 4: Solution VIDEO INFOGRAPHICS

## Slide 5: Objectives
To convey the correct information of each unit and proper overview of each unit.
To visualize the entire admissions test procedure at a glance.
01
03
To make an effective and efficient admission process
To avoid confliction of different units admission criteria.
02
04

## Slide 6: Progress Summary of Week 01
Date/Location: 18-Nov-2022 (Google Meet)
Attendees: Israt Jahan Munny (IJM), Rifat Ara (RA), Jannatul Ferdaws Amrin (JFA), Shahrin Khan (SK), Ikramul Islam Emon (IIE), Md. Asoad Alvi YaNur Saom (AAYS), Md. Anayet Ullah (AU)
Duration: 11:00pm - 11:35pm
Decisions:
                Brainstorming
                Group name and Idea Selection
                Resource collection
                Roles and Responsibilities Distribution
                Budget Estimation
                Meeting Schedule

## Slide 7: Result
                Roles & Responsibilities:
                Producer: Dr Mohammad Zahidur Rahman.
                Project Manager: Amrin
                Graphic Designer: Shahrin
                Script Writer: Saom, Anayet, Munny
                Voice Artist: Emon
                Sound Designer: Rifat
                Required Tools:
                Design: Inkspace, GIMP, Canva
                Audio: Audacity, KDENlive, Ardour6
                Management: Trello, GanttProject.

## Slide 8: Result
                Gantt Chart:

## Slide 9: Result
                Work Break-Down Structure:

## Slide 10: Result
                Group Name:
                Bit to Byte Production
                Logo Design:

## Slide 11: Result
                Budget Estimation:

## Slide 12: Hindrance Language Selection Budget Estimation

## Slide 13: Solutions
Depending on individual work

## Slide 14: Progress Summary of Week 02
Date/Location: 23-Nov-2022 (Google Meet)
Attendees: Israt Jahan Munny (IJM), Rifat Ara (RA), Jannatul Ferdaws Amrin (JFA), Shahrin Khan (SK), Ikramul Islam Emon (IIE), Md. Asoad Alvi YaNur Saom (AAYS), Md. Anayet Ullah (AU)
Duration: 10:00pm - 10:40pm
Decisions:
Collect necessary information, materials for project content and design
Designing the outline
Formatting the content
Writing the scripts
Learning the uses of tools as well as design some parts of infographics

## Slide 15: Result
Flowchart:

## Slide 16: Assigned member in Documentation and Design part
Collect information on faculty of social sciences and faculty of law
JFA
Collect information on faculty of Arts and Humanities and faculty of Business studies
Collect information on faculty of Biological Sciences
Collect information on faculty of Mathematics and Physics
IIE
MAAYS
IJM
01
02
03
04
Logo Design
Collect necessary materials for design
SK
MAU
04
05
06
RA
starting design some parts of infographics

## Slide 17
Initial Version of Infographics:

## Slide 18: Hindrance Selection of Color & themes Writing Scripts

## Slide 19: WHOA!
We have arrived in our THIRD week!!!!

## Slide 20: Planning of Week 03
04.
Schedule a meeting to distribute works among team
02.
Implementing the design in the video tools
03.
Synchronizing the audio
01.
Writing the Scripts (Due on Week 02)
Adding text content and voice in the video
05.

## Slide 21: AHH!. Slide has Ended

## Slide 22: THANKS!

## Slide 23: Do You have any QUESTIONS
??????
Search